## Overview
Sample Campus Project Plan
Campus Name: San Bernardino Valley College
Headcount of students enrolled: 12,741
Headcount of faculty teaching: 561
Campus strategic priority that aligns with AB 798: Access, Student Success, Leadership & Professional Development Overview - San Bernardino Valley College (SBVC) is part of the San Bernardino Community College District which serves the ethnically diverse Inland Empire region and is a designated Hispanic Serving Institution. The campus serves an area that includes some of the lowest achieving K-12 institutions in the state (Strategic Plan, 2014-2019, http://www.valleycollege.edu/about-sbvc/offices/office-research-planning/). The majority of SBVC students (76%) receive some form of financial aid (SBVC Research, Planning, & Institutional Effectiveness). During spring 2018, and under the purview and support of the Academic Senate, SBVC updated its Textbook Affordability plan which was approved by both the Academic Senate, and College Council. College Council includes collegial campus representation and the body is co-chaired by the college President and Academic Senate President. The Associated Student Government also voted to support these efforts by the Academic Senate. During spring 2016, the Academic Senate passed SP16.01 Textbook Affordability and Open Education Resources Resolution which continues to be in effect along with the responsibilities of the Textbook Affordability Campus Coordinator. This updated Textbook Affordability Plan includes the following overarching goals: • Increase the use of OER to save students money on textbooks in transfer, basic skills, and vocational courses • Facilitate and support professional development opportunities to assist faculty in the curation, and adoption of OER and open pedagogy • Institutionalize the Textbook Affordability Plan as a permanent working document.
SBVC is a AB 798 recipient, having been awarded $31,000. During the AB 798 first round, SBVC more than tripled its OER sections and faculty in over 18 different disciplined saved students approximately $413,000 on textbook costs from fall 2016 to spring 2018.
Campus Partner (if applying for the first time): | N/A
Project Objectives
1. SBVC faculty will adopt OER in at least 32 new sections by spring 2019 and this number will double in 2019-2020 in order to increase accessibility to open and low cost instructional materials for SBVC students to save them money on the high cost of textbooks and increase student access and success.
2. SBVC Textbook Affordability Campus Coordinator will provide leadership and assist in the facilitation of OER professional development activities, OER related communication, and implementation of OER policies to ensure that faculty and students have access to OER information and resources during 2018-2019 and 2019-2020.
3. SBVC Textbook Affordability Campus Coordinator will provide leadership and facilitate activities to support the institutional implementation of a permanent and sustainable SBVC Textbook Affordability Plan by spring 2020.
4. SBVC Academic Senate will encourage and foster an institutional and collegial climate that supports institutional efforts and processes for the adoption of low cost and free open educational resources.
Measures of Success: List the top metrics you will track to compare with your objectives
1. TACC and the Office of Research, Planning and Institutional Effectiveness will track the number of course-section adoptions, and financial savings per course sections.
2. Office of Research, Planning and Institutional Effectiveness will complete student surveys measuring student access to OER and satisfaction with OER materials.
2. Office of Research, Planning and Institutional Effectiveness will complete faculty surveys measuring faculty access to OER and satisfaction with OER materials.
4. Bookstore will track student purchases of print copies of OER.
5. Library will track student check-out of print copies of OER.
6. Webpage data analytics will be used to track page views and visitors to the SBVC OER website.
7. Professional Development Coordinator will track number of professional development activities, and the number of attendees at each event.
8. Professional Development Coordinator will provide satisfaction surveys to attendees and participants of OER related activities.
9. Faculty Handbook will be updated to include information regarding SBVC Textbook Affordability Plan.
10. Academic Senate, College Council, and Board of Trustees will support efforts and activities encouraging institutional support for OER.
11. Instititutional Strategic Goals and Initiative related documents will include information about the SBVC Textbook Affordability Plan.
Campus Readiness: List the existing aspects of your campus culture, organization, resources, and support services that will help support faculty adoption of low/no cost course materials on your campus.
Examples: Campus's faculty development center will provide an excellent organization and trusted resource to support faculty learning about OER and getting the support to adopt the resources in their courses.
1. Academic Senate has a strong campus presence and supports academic matters related to the institutional strategic initiatives. The Academic Senate will faciliate the permanent implementation of the SBVC Textbook Affordability Plan.
2. Academic Senate will support the work of the OER-Ad Hoc Academic Senate campus committee, and ZTC Degree Workgroup.
3. Textbook Affordability Campus Coordinator will communicate and facilitate access to OER materials and information via the college OER website, OER Canvas shell, OER social media, and OER newsletters.
4. Textbook Affordability Campus Coordinator and the Zero Textbook Cost Degree Grant Team will work together to implement a ZTC AA Liberal Arts Social and Behavioral Science degree and facilitate processes to develop other ZTC degrees and/or certificates.
5. Textbook Affordability Campus Coordinator will network with OER organizations and local higher learning institutions regarding OER partnerships and this includes attending OER meetings, and conferences.
6. Associated Student Government will assist students who need access to digital OER by providing them access to the internet and computers in the Student Life lounge.
7. Professional Development Coordinator and the Professional Development Committee will organize OER professional development activities for faculty and staff.
8. Office of the Vice President of Instruction will provide OER outreach to faculty chairs through faculty chair meetings and include OER information in the Faculty Handbook.
9. Library will provide access to print copies of faculty adopted OER materials via the Reserve Desk, allowing students to check-out OER materials for short periods.
10. Librarians will assist in the curation of OER materials for inclusion at the OER college website.
11. Librarians will assist faculty with the submission of OER materials to MERLOT.
12. Computer Lab and Library provides student access to the internet and printers, allowing them to print OER instructional materials.
13. Bookstore will sell low cost print copies of OER adopted by faculty.
14. Bookstore maintains booktore website with information about required instructional materials for each class section.
16. District Print Services will provide free print copies of OER to faculty to use as desk copies. Print copies can be forwarded to the bookstore, and library and when appropriate for student use in the classroom.
17. District Technology and Educational Support Services will support college campus technological needs including the maintance and analytics of the OER website, OER Canvas shell, and other online OER campus efforts.
18. District Technology and Educational Support Services maintains Canvas shells for all class sections. Faculty can provide links to .pdf documents and OER weblinks for student access and ability to print hard copies.
19. Online Programs Committee serves as a conduit of information for faculty, administration, and students related to online learning. Online Programs Committee assists in the dissemination of online preparation and literacy resources that allow students to assess online skills. The Online Programs Committee can assist faculty with accessibility concerns and issues, copyright information, and information regarding any distance education curriculum modification requirements which involve the use of OER.
20. Office of the Vice President of Student Services oversees student success programs including management of the Student Success Initiative. TACC will work with the Vice President of Student Services to identify programs such as Puente, Tumaini, Valley Bound Commitment, STAR/Trio, EOPS, etc. with the intent to utilize existing resources to provide outreach and assistance to students in their use of OER materials, including the dissemination of free OER hard copies, access to the internet, and the use of existing student services funds to print OER materials. OER outreach and assistance will contribute to student success among underprivileged students who are often at risk for dropping classes, academic probation, and dropping out of college partially due to not having the financial resources to purchase instructional materials or access to affordable textbooks.
21. Disabled Student Programs and Services will work with faculty who need accessibility assistance regarding the adoption of OER and they will provide accessibility support to registered DSPS students who are enrolled in classes in which OER is being utilized.
22. Basic Skills Committee oversees implementation of the campus Basic Skills Plan. TACC will work with the Basic Skills Committee to continue to identify resources to provide outreach and assistance for the adoption and use OER in developmental courses. The use of OER by faculty and students will enhance student learning in developmental classes because it will simultaneously facilitate and teach technology related skills which students need as they transition to transfer level courses.
23. Honors Program maintains a webpage and Canvas shell which are used to disseminate information to students about the honors program. Honors Program Coordinator and the Honors Program counselor can assist in the dissemination of OER information to both faculty teaching honors classes and students enrolled in honors classes.
24. Faculty who have developed or curated OER will serve as OER ambassadors.
25. Faculty Handbook includes OER adoption information for faculty. This document is updated regularly to include OER information and updates.
26. Flex Days, and Adjunct Orientations regularly include speakers, workshops, and professional development activities. Various constituency groups such as the Professional Development Committee, Student Support Services, Instruction Office, and the Academic Senate among others are consulted regarding agendas and activities. OER related activities will be incorporated during these campus wide events which occur every semester.
27. Fall and Spring In-Service include faculty meetings that will be utilized to disseminate OER information and outreach efforts to full time faculty.
28. Office of Marketing and Public Relations has established communication channels with students via college website, and SBVC social media allowing for the dissemination of OER information. The SBVC college website includes an on-going OER marketing and outreach banner.
29. Office of Research, Planning, and Institutional Effectiveness oversees faculty and staff requests for data collection and analysis and will measure and evaluate campus OER usage.
Campus Challenges: Describe some of the existing challenges to faculty adoption of low/no cost course materials on your campus that your proposed textbook affordability program will address.
The following are anticipated challenges to the adoption of OER at SBVC as it implements the second round of AB 798 funding. Many disciplines lack OER instructional materials in their disciplines, particularly in non-introduction courses, and vocational courses. Additionally, some of the current OER materials need to be updated by discipline experts and made available via the main OER repositories and MERLOT. Therefore, networking with the OER community to share resources across institutions will become much more important in the next few years. While SBVC faculty now have access to professional development OER activities and resources, the time commitment to covert classes to partial and/or complete OER is still significant. The campus for the last few years has been working without an institutional grant writer and director. Hopefully, this situation will be resolved in the next academic year and the college can qualify for additional OER grants to support faculty in adopting OER in their classes. The institutionalization of OER funding through Program Review and Student Success funds will also assist in some of these challenges. Faculty who adapt OER come to this process at different stages and therefore it is crucial that continual outreach OER efforts remain in place. Some faculty lack access to converting pdf documents for purposes of making documents accessible to students and modification. Therefore, the district technological services need to invest in more time or resources to ensure that faculty are aware of the technological services that support faculty in these endeavors. There are faculty who have developed their own intellectual content but are reluctant to share materials openly and collaborative departmental efforts need to be nurtured to allow faculty opportunities to at least share their resources within small communities. For profit publishers continue to market products to counter the use of OER by faculty and therefore providing faculty with information to the OER materials that are available in their disciplines is crucial. Finally, the processes regarding the communication of zero textbook cost sections to students in a timely fashion at this time is still a challenge as college administrators, faculty, and staff work out the processes to abide by the new SB 1359 regulations. As these processes are worked out, this will on the other hand provide opportunities for the college to consider publishing low-cost sections in the online schedule of classes. Regardless of these challenges, the Academic Senate has identified support among faculty, administrators, staff, and students for the implementation of this updated Textbook Affordability Plan and there is agreement that these challenges are not significant barriers for the college to continue to increase its ZTC and low cost textbook section offerings through the use of OER.

## Project Team
Project Team
Coordinator(s)
Name | Email | Phone |  | Department
Romana Pires | rpires@valleycollege.edu | (909) 384-8602 |  | TACC/Sociology
Working Group Team members
Name | Email | Phone |  | Department
Jennifer Bjerke | jbjerke@sbccd.cc.ca.us | (909) 384-8653 |  | ZTC Degree Coordinator/Geography
Raymond Carlos | rcarlos@valleycollege.edu | (909) 384-8253 |  | Director of Student Life
Laura Cross | lcross@sbccd.cc.ca.us | (909) 384-8603 |  | Administrative Secretary
Virginia Diggle | vdiggle@sbccd.cc.ca.us | (909) 384-4085 |  | Contract & Liability Specialist
Christie Gabriel | cgabriel@sbccd.cc.ca.us | (909) 384-8907 |  | Senior Research Analyst
Andrea Hecht | ahecht@sbccd.cc.ca.us | (909) 384-8974 |  | ZTC Degree Counselor/Counselor
Rick Hrdlicka | rhrdlicka@sbccd.cc.ca.us | (909) 384-8656 |  | Director Campus Technology Services
Dr. Terri Long | tlong@sbccd.cc.ca.us | (909) 384-1685 |  | Interim Vice President Instruction
Dr. Marie Mestas | mmestas@sbccd.cc.ca.us | (909) 384-8576 |  | Professor, Library
Rania Hamdy | rhamdy@valleycollege.edu | (909) 384-8623 |  | Professional Development Coordinator
Ron Hastings | rhastings@valleycollege.edu | (909) 384-8542 |  | Director of Library and Learning Support
Dr. Wallace Johnson | wjohnson@sbccd.cc.ca.us | (909) 384-8603 |  | AB 798 Manager, Division Dean
Rhiannon Lares | rlares@sbccd.cc.ca.us | (909) 384-4903 |  | Instructional Technology Specialist
Girija Raghavan | graghava@sbccd.cc.ca.us | (909) 384-8950 |  | Accountant
Dr. James Smith | jasmith@sbccd.cc.ca.us | (909) 384-8600 |  | Dean Research, Planning & Institutional Effectiveness
Project Partners
Name | Email | Phone |  | Organization & Responsibilities
Basic Skills Committee | jbackey@sbccd.cc.ca.us | (909) 384-8653 |  | Basic Skills Plan
SBVC Bookstore | rvega@follett.com | (909) 384-3250 |  | OER Print Materials
Academic Senate | chuston@sbccd.cc.ca.us | (909) 384-8574 |  | Academic Recommendations
Associated Students |  | (909) 384-4474 |  | Student Representation
Disabled Student Programs and Services | mmilliga@sbccd.cc.ca.us | (909) 384-8949 |  | Disabled Students Services
Honors Program | ablacksher@sbccd.cc.ca.us | (909) 384-8667 |  | Faciliation of Honors Courses
Library | rhastings@valleycollege.edu | (909) 384-8542 |  | College Library Services
Office of Marketing and Public Relations | pbratulin@valleycollege.edu / | (909) 384-8978 |  | Communication & Messaging
Office of the Vice President of Instruction | tlong@sbccd.cc.ca.us | (909) 384-1685 |  | Instruction Leadership
Office of the Vice President of Student Services | sthayer@sbccd.cc.ca.us | (909) 384-8992 |  | Student Services Leadership
Office of Research, Planning and Institutional Effectiveness | jasmith@sbccd.cc.ca.us | (909) 384-8907 |  | Planning, Research
Professional Development Committee | rhamdy@valleycollege.edu | 909-384-8623 |  | Professional Development Leadership
SBCCD Technology and Educational Support Services | rlares@sbccd.cc.ca.us | (909) 384-4903 |  | Technology Leadership & Support
Project Governance Structure
Executive Sponsors (Insert name, title) |  |  | What major decisions from these sponsors are needed for your project?
SBVC Academic Senate |  |  | Textbook Affordability Plan Approval and Facilitation
SBVC College Council |  |  | Textbook Affordability Plan Collegial Consultation
Board of Trustees |  |  | AB 798 Contract and Budget Approval
Bruce Baron, Chancellor |  |  | AB 798 Contract and Budget Approval
District Assembly |  |  | District Board Policy Change College Consultation
Associated Student Government |  |  | Textbook Affordability Plan Collegial Consultation
Other Shared Governance Individuals or Groups (Insert name, title) |  |  | What major decisions from these sponsors are needed for your project?
Academic Senate |  |  | Textbook Affordability Plan Updates and Facilitation
College Council, (Advises College President) |  |  | Textbook Affordability Plan Updates and Facilitation
SBCCD Board of Trustees |  |  | District Policy and Budget Expenditure Approvals

## Communications & Outreach
Communication and Outreach Plan
The Communication and Outreach plan will help you determine how you will leverage a variety of activities to increase low/no cost course awareness, knowledge, and interest across different stakeholder groups at your institution. Edit and fill out as many of the cells of the template below to assist you in your AB 798 RFP initiative planning. The column headings provide the aspects that you could consider, and the rows provide the potential stakeholders that might be important to include in your communications plan. You may use the same activity for multiple stakeholder groups. All rows need not be filled out; however, they are included for you to consider as many campus stakeholders in your AL$ communications' plan as possible.
POTENTIAL Stakeholders | Key Value Proposition (Refer to your key attributes on the overview tab) | Desired Outcome/Action | Activity to be Executed | Timing | Responsible Party | Measure of Success
Instructional Faculty | Access and OER adoption in transfer, vocational, and development courses | Faculty will have access to OER information and updates | OER Newsletter, Flyers, Blog, Departmental Emails, Twitter, OER Canvas Shell | Fall 2018, Monthly | TACC, ZTC Degree Coordinator | 20% increase in adoption of OER sections semester-semester
Campus | Access and OER adoption in transfer, vocational, and development courses | Faculty, Students, Staff | OER College Website | Fall 2018, Monthly | TACC, Librarians | Increased webpage views/visitors
Students | Access to Zero Textbook Cost Sections | Streamline SB 1350 Reporting Processes and Student OER Communication | OER Announcements via College Social Media Channels, and Website, Web Advisor | Fall 2018 on-going, every semester | Marketing Office and Instrucstion Office | Annual Student OER Survey
Students | Access to Student Support Services | OER Information to Students | Student Emails Regarding OER Student Services Resources | Fall 2018 on-going, every semester | Marketing Office, Associated Student Government, Library, ZTC Counselor | Annual Student OER Survey
Faculty Chairs | Professional Development, Faculty access to OER and adoption | OER Information to Faculty | Faculty Chair Meeting OER Presentations | Fall 2018 and as needed | TACC | Increased faculty adoption of OER
Academic Senate | Implementation of Textbook Affordability Plan | OER Information to College Representatives | Academic Senate OER Presentation | 2018-2019 and 2019-2020 | TACC | Increased adoption of OER,and faculty inquiries. Institutionalization of permanent Textbook Affordability Plan
Associated Student Government | OER Student Access | OER Information to Students | ASG OER Presentation | Fall 2018 | TACC | Motion or resolution to support permanent Textbook Affordability Plan
Students | OER Student Access | OER Information to Students | ASG OER Flier Distribution During Welcome Week | 2018-2019 | ASG | Increased student use of OER campus resources
College Council | Implementation of Textbook Affordability Plan | OER Information Updates to College Representatives | College Council Meeting Information | Spring 2019 | TACC | Increased adoption of faculty OER, increase in possible funding sources for OER activities, student access
Instructional Deans | Professional Development, Faculty OER Access | OER Information Updates to Instructional Division Deans | Instructional Cabinet | Spring 2019 | TACC | Increased adoption of OER, deans share information with faculty
Student Services Faculty, Managers, and Staff | OER Student Access | OER Information Updates to Student Services Faculty and Managers | Student Services Meeting | Spring 2019 | TACC | Increased student access to hard copies and online OER
FT Faculty | Faculty OER Adoption/Use | OER Information Updates to Campus Full Time Faculty | Announcement During In-Service Faculty Meeting | Spring 2019 | TACC | Increased FT faculty OER adoption
PT Faculty | Faculty OER Adoption/Use | OER Information Updates to Campus Part Time Faculty | Announcement During Adjunct Orientation | Spring 2019 | TACC | Increased PT faculty oer adoption
Students | OER Student Access | OER Information to Students | OER Flier Distribution to Students Through Student Success Offices Regarding Student Support OER Resources | Fall 2018, on-going | TACC & Student Services Coordinators or Administrative Assistants | Increased students use of on-campus resources lacking access
Honors Faculty, and Honors Students | OER Adoption/Use | OER Information to Honors Faculty and Students | Incorporate information in Honors Canvas Shell | Spring 2019 | TACC an Honors Program Coordinator | OER Adoption/use among honors faculty
Students | OER Student Success | OER Instructional Materials Information | Flier Distribution to Students Through Bookstore | Spring 2019 | TACC and Bookstore Staff | Increased students use of on-campus resources lacking access
Students | OER Student Access | OER Instructional Materials Information | Flier Distribution to Students through Campus Library | Spring 2017 and On-Going | TACC and Library Staff | Increased student use of on-campus resources lacking access
Students | OER Student Access | Student Information Updates In Arrowhead News | OER Announcement and Update | Spring 2019 | TACC and Faculty Advisor | Increased OER student awareness
Faculty | OER Faculty Adoption | OER Updates Faculty Information and Processes | Faculty Handbook OER Information | Spring 2019 | TACC, Academic Senate, VPI | Increased OER Adoption/Use
Faculty | OER Faculty Adoption | Textbook Affordability Plan | OER Handbook and Development of Permanent Textbook Affordability Plan Campus Announcement, and Faculty Handbook Information | 2018-2019, 2019-2020 | TACC, Academic Senate, College Council | Institutionalization of Textbook Affordability Plan
Faculty | OER Faculty Adoption | MERLOT Flyer on how to use and submit OER to MERLOT | Place fliers in faculty mailboxes and include in OER College Website | Spring 2019 | TACC | Increased adoption/use, number of inquiries
Faculty | OER Faculty Adoption | Announcements | Email faculty to announce professional development opportunities | Fall 2018, on-going | TACC, Professional Development Coordinator | Increase in faculty adoption of OER and ZTC Sections
Students | OER Student and Faculty Access | Campus OER Logo | Graphic Arts Students create OER logo for SBVC | 2018-2019 | TACC, Faculty Chair, Division Dean Humanities Division | Student OER Survey
Faculty | OER Faculty Access | Announcements | Email information regarding OER webinars and OER conferences | Fall 2018, on-going | TACC, ZTC Degree Coordinator | Increase in faculty adoption of OER and ZTC Sections
Faculty | OER Student Access | Announcements | SB 1359 Reporting Emails | Fall 2018, on-going | TACC, Instruction Office | Student OER Survey

## Training
Training and Professional Development Plan
The Training and Professional Development plan will help you support your faculty understanding the value of adopting free and open educational resources and the impact it can have on student success. Edit and fill out as many of the cells of the template below to assist you in your AB 798 RFP initiative planning. The column headings provide the aspects that you could consider, and the rows provide the potential stakeholders that might be important to include in your communications plan. You may use the same activity for multiple stakeholder groups. All rows need not be filled out; however, they are included for you to consider as many campus stakeholders in your AL$ communications' plan as possible.
POTENTIAL Stakeholders | Topic for Training | Types of training | # of people invited | Schedule | "Trainers" | Measure of Success
Faculty | Introduction to OER | One-One Faculty Training | One-One Faculty | Fall 2018, on-going | TACC, ZTC Coordinator, ZTC Librarian, Technology Specialist | Faculty OER Survey
Adjunct Faculty | OER and Open Pedagogy | Adjunct Orientation Workshop | 40-50 Faculty | Spring 2019, Spring 2020 | TACC, Instructional Technology Specialist | Faculty OER Survey
Counseling Department | OER and Student Success | Presentation Workshop | 20-25 Counseling Faculty | Fall 2018 | TACC, ZTC Counselor | Faculty and Student OER Survey
Campus Faculty | Evaluating OER Resources | Presentation Workshop | 25-30 Campus Faculty | Spring 2019 Flex Day | TACC, Professional Development Coordinator | Increase in OER adoption
Instructional Divisions Faculty | MERLOT and Authoring OER | Presentation Workshop | Division Faculty | Fall 2018, ongoing | TACC, ZTC Coordinator | Increased number of faculty adopting OER in each division/discipline across campus
Regional Faculty | OER and Best Teaching Practices, Challenges, Successes | Great Teachers Retreat | 60-75 Faculty from Regional Community Colleges | Spring 2019 or Spring 2020 | TACC, Professional Development Coordinator | Event Feedback Survey
Campus Faculty | OER Webinars/OER Website | Self-Paced Online Modules | Individual Faculty | Fall 2018, on-going | TACC, Librarians | Increase in number of faculty adopting OER
Campus Faculty | OER Webinars/OER Website | Live and Recorded Webinars | Individual Faculty | Fall 2018, on-going | TACC, Librarians | Increase in number of faculty adopting OER
Campus Faculty | Using Institutionally Licensed Resources as OER | Workshop | Campus Faculty | Fall 2018, on-going | Librarians | Participation Satisfaction Survey
Campus Faculty | How do I Find OER? | Self-Paced Canvas Shell | Campus Faculty | Fall 2018, on-going | TACC | Increase in number of faculty inquiries, number of faculty adopting across discipline
Campus Faculty | OER Basics for Faculty | Self-Paced Canvas Shell | Campus Faculty | Fall 2018, on-going | TACC | Increase in number of faculty inquiries, number of faculty adopting across discipline
CTE Faculty | Skills Commons Repository | Workshop | CTE, Workforce Development Faculty | Fall 2018 | TACC | Participant Satisfaction in Training, # of attendees
Transfer Faculty | Open Stax Basics Repository, OEI and OER | Workshop | Transfer Disciplines Faculty | Spring 2019 | ZTC Coordinator | Participant satisfaction in Training, # of attendees
Campus Faculty | Canvas Instructional Design and OER | Workshop | Campus Faculty | Spring 2019 or Fall 2019 | Professional Development, Technology Design Specialist | Particpant satisfaction in training, # of attendees
New Faculty Orientation | OER Handbook and Faculty Handbook | OER Incorporated into Existing New Faculty Orientation | 1-10 Faculty | Fall 2018, on-going | Professional Development/OER Faculty Ambassadors | Participant satisfaction survey
Department Instructional Faculty | Faculty Chair Department Meetings | Faculty Discipline Discussions | Varies, Campus Faculty | Fall 2018, on-going | Faculty Chairs, Division Deans | Faculty OER Survey
OER Ad Hoc Committee and/or ZTC Degree Workgroup | Textbook Affordability Plan Implementation Stragies | Collaboration Meetings | 10-15 Faculty | 2018-2019, 2019-2020 | Academic Senate | Successful Implementation of Sustainable and Permanent Textbook Affordability Plan
OER Ad Hoc Committee and/or ZTC Degree Workgroup | Textbook Affordability Plan Institutional Funding Stragies | Collaboration Meetings | 10-15 Faculty | 2018-2019, 2019-2020 | Academic Senate | Successful Implementation of Sustainable and Permanent Textbook Affordability Plan
Campus Faculty | OER and Accessibility Issues | Faculty Workshop | Campus Faculty | Fall 2018, on-going | DSPS | Number of attendees, participant satisfaction survey
OER Ad Hoc Committee | Open Ed Conference or Similar Events | OER Faculty Meetings | 1-10 Faculty | Fall 2018, on-going | OER Ad Hoc Committee, TACC | Increase in faculty OER adoption, increase in access to student OER access

## Help and Support Services
Help and Support Services Plan
The Help and Support Services plan will help your campus answer questions, help access to the free and open educational resources, help resolve issues, and provide other help and support during the implementation of your textbook affordability program. Edit and fill out as many of the cells of the template below to assist you in your AB 798 RFP initiative planning. The column headings provide the aspects that you could consider, and the rows provide the potential stakeholders that might be important to include in your communications plan. You may use the same activity for multiple stakeholder groups. All rows need not be filled out; however, they are included for you to consider as many campus stakeholders in your AL$ communications' plan as possible.
POTENTIAL Stakeholders | Type of Help and Support Services | # of people available to deliver help services | Schedule | Help and Support Service Providers | Measure of Success
Faculty and Students | College OER Website Data Analytics and Template Modifications | One | Fall 2018, monthly | TESS District IT Staff | TACC and Librarians receive regular service
Campus Faculty | College OER Website Updates | One-Two | Fall 2018, monthly | TACC and Librarian | Faculty satisfaction survey, webpage usage
Campus Faculty | OER Curation and Adoption Q&A | One-Five | Fall 2018, on-going | TACC and OER AB 798 Team | Faculty OER survey
Students | ZTC class section help | One-Ten | M-F Daily | District Help Desk, TACC, Instruction Office, Division Deans, Instructional Faculty | Student OER Survey
Students and Faculty | Print OER | One-Five | M-F Daily | Bookstore, District Print Shop | Student and Faculty OER Surveys
Faculty | OER and Accessibility Issues | One-Three | Fall 2018, on-going | DSPS Counselors | Faculty OER survey
Faculty | Print hard copies of OER materials for faculty, library use | Three-Five | During faculty textbook order season each semester (Nov, April) or as needed | SBCCD Copy Center | Number of faculty requesting and receiving OER copies
Faculty | Instructional Design, and Canvas Support | Three-Five | Fall 2018, on-going | TACC, Professional Development Coordinator, Librians, Technology Instructional Specialist | Faculty OER survey
Students | Assisting DSPS students with accessibility issues and OER | Three-Five | M-F Daily, During DSPS Hours | DSPS Support Staff | Number of students using DSPS Center for assistance with OER
Students | Library OER print materials Reserve Desk | Two-Three | Fall 2018, Library daily hours | Library Support Staff | Student OER Survey
Campus Community | Implementation of sustainable and permanent Textbook Affordability Plan | Campuswide | 2018-2019, 2019-2020 | TACC, OER Ad Hoc Committee, ZTC Degree Workgroup, Academic Senate, College Council | Institutionalization of Textbook Affordability Plan
Faculty | OER Professional Development | Approximately 5-10 | Fall 2018, on-going | Professional Development Coordinator, Professional Development Committee, TACC, ZTC Workgroup, OER Ad Hoc Commmittee, District Technology Support | Increase in faculty adopting OER, Faculty OER survey
Faculty and Students | Student online literacy resources, faculty concerns, issues regarding using OER online | Approximately 5-10 | Fall 2018, on-going | Online Programs Committee, District TESS Services | Access to information, number of resolved issues
Faculty | Use of OER by basic skills students | Approximately 10 | Fall 2018, on-going | Basic Skills Committee | Access to information, number of resolved issues
Campus Community | Access to OER data and analysis | 2-3 Support Staff | Fall 2018, on-going | Research Office | Measurement of OER activities
Students | Access to computers and internet | Support Staff | Fall 2018, daily | Library Support Staff and ASG Student Life Lounge | Student OER Survey
Students | Access to OER Information | Campuswide | Fall 2018, on-going | ASG, Student Support Services, TACC | Student OER Survey
TACC, OER Ad Hoc Committee | Administrative Support | 3-5 Support Staff | Fall 2018, on-going | Accountant, Administrative Assistant, Contracts, Management Oversight | Successful implementation of AB 798 deadline and Plan
Campus Community | Institutional Collegial Processes | Campuswide | 2018-2019, 2019-2020 | Program Review, Grant Support, Student Success Initiative | Institutionalization of OER funds

## Discovery to Distribution
Plan for Discovery, Curation, and Distribution of Digital and Print Course Materials
The plan to enable faculty and students to find, organize, and acquire the digital and print versions of the courses materials plan will be essential for the successful implementation of your textbook affordability program. Edit and fill out as many of the cells of the template below to assist you in your AB 798 RFP initiative planning. The column headings provide the aspects that you could consider, and the rows provide the potential stakeholders that might be important to include in your communications plan. You may use the same activity for multiple stakeholder groups. All rows need not be filled out; however, they are included for you to consider as many campus stakeholders in your AL$ communications' plan as possible.
POTENTIAL Stakeholders | Strategies for Finding OER | Strategies for Curating OER | Strategies for Distributing OER | Getting Print Copies | Measure of Success
Students | Web-Avisor, Public Online Schedule of Classes, OER College Website, Bookstore Webpage, Student Support Services, Library, Print Copies of OER, Digital Copies of OER | Faculty communicate with students instructional materials via class syllabus, Canvas shell, campus bookstore | Bookstore, Faculty, Library, Canvas | Bookstore, Computer Lab and Printers, Library | Increase in student success rates in sections using OER
Students | Campus Outreach Fliers, SBVC Social Media, OER Student Video, College Website OER Banner | TACC and OER Ad Hoc Committee, ZTC Degree Workgroup develop strategies to market OER information to students | Faculty disseminate information, campus fliers, college OER website, bookstore webpage, Library reserve desk, Student Life, ASG, Canvas, Bookstore, Library, Print Copy Center, Printers in Computer Lab and Library, Student Services for select student populations | Faculty distribution via Canvas or other CMS, Faculty distribution of print copies in select sections, Student Services: DSPS, Student Life Computer Lounge, STAR, EOPS, Valley Bound, etc. | Increase in student success rates in sections using OER
Librarians | Cool4ed.org, MERLOT, college OER website, OER repositories, collaboration with OER organizations | Library facultym and TACC Curate college OER website | TACC, Professional Development Coordinator, OER Ad Hoc Committee, ZTC Degree Workgroup | Library Reserve Desk, Copy Center | Number of students and faculty utiling OER webpage, hard copies
Faculty | Professional Development, OER College Website, Faculty Collaboration Meetings, Outreach, Marketing, Technology Instructional Specialist, Librarians, Division Deans, MERLOT, COOL4Ed | Library Faculty, TACC Coordinator, Professional Development Coordinator, Technology Instructional Specialist | TACC, Bookstore, Print Shop, Canvas, Librarians, Professional Development, Faculty Chairs, Deans | Bookstore, SBCCD Print Center, OER Publishers, Open Stax, OER College Website | Continued use of OER by faculty, new adoption of OER by faculty
Student Support Staff | Collaboration with TACC and Professional Development, OER Website | Library Faculty, TACC Coordinator, Professional Development, college OER website, MERLOT | OER Fliers and Outreach Literature, Division Meetings, Department Meetings | SBCCD Print Shop, OER Publishers, Bookstore | Increase in student access to OER information
Administrators | Collaboration with TACC, OER Ad-Hoc Committee, and Professional Development, OERCollege Website | Library Faculty, TACC Coordinator, Professional Development, college OER website, MERLOT | Division meetings, College Council Meetings, Instructional Cabinet Meetings | SBCCD Print Shop, OER Publishers, Bookstore | Increase in administrator access to OER nformation, increase in faculty adoption of OER
Campus Bookstore Staff | Collaboration with TACC, OER Ad Hoc Committee, and Professional Development, OER Website, Faculty adopting OER, Copy Center, OER Publishers | Library Faculty, TACC Coordinator, Professional Development, college OER website, MERLOT | On-Campus Bookstore, Online Bookstore Webpage | Faculty adopting OER, OER Publishers, Copy Center | Student access to hard copies of adopted OER
Faculty Chairs | Collaboration with TACC and Professional Development, OER Website | Library Faculty, TACC Coordinator, Professional Development, OER college website, MERLOT | Faculty Chair Meetings, Professional Development, TACC, OER Website | Copy Center, OER Publisher, Bookstore | Increase in faculty access to OER information, increase in faculty adoption of OER across campus specific disciplines and departments
Professional Development Coordinator | Collaboration with TACC and OER Ad Hoc Committee, OER Manager | Collaboration with Librarians, and TACC to curate OER materials for college OER website | Professional Development OER activities | Copy Center, OER Publisher, Bookstore | Participant satsifaction surveys, increase in faculty adoption of OER and low cost textbooks
Campus Textbook Affordability Coordinator | Collaboration with Professional Development Coordinator, AB 798 and A$L Coordinators, OER Ad Hoc Committee, Academic Senate, District Assemble | Collaboration with Librarians to curate OER materials for college OER website, AB 798 and A$L coordinators, OER list servs. | Outreach Activies to Faculty, and Students, Professional Development Activities, Meetings with Stakeholders | Copy Center, OER Publisher, Bookstore | Increase adoption and use of OER and low cost textbooks by both faculty and students

## Tech.Facility.Policy.Resource
Technologies, Facilities, Policies, and Resources
Technology Requirements: List any technology requirements that will be necessary to successfully execute your plan.
Example: Distribute communications and outreach through campus listserv's to faculty, staff, and students
Example: Use campus LMS to provide access to the OER and library resources used to substitute for expensive print textbooks
Example; Use campus portals for students and faculty to provide access to the help and support services
1. District Technology Services: modify OER webpage template on the OU Campus portal, grant user permission access, provide data analytics for OER webpage.
2. District Technology and Educational Support Services: update Help Desk with OER FAQs for faculty/students, create and maintain Canvas shells for all sections so faculty can provide student access to OER for online use or printing, support services for SB 1359 ZTC section reporting (and possibly low cost section reporting).
3. Librarian(s): training in the use of OU Campus Portal to develop and curate OER webpage for faculty and student use and printing.
4. Marketing Support: provide social media outreach to students, faculty, and campus community.
5. Bookstore: post OER information on bookstore webpage to provide student access to low cost OER materials.
Facility Requirements: List any facility requirements that will be necessary to successfully execute your plan.
Example: Library will provide a "special reference desk" for supporting faculty and students with finding and using OER
Example: Campus center for students with disabilities are prepared to support use of OER
Example: Bookstore will provide a special location in bookstore for information about the OER resources
1. Bookstore: space for OER information low cost hard copies and OER information for students and faculty.
2. Library: space in the Reserve Desk section for OER information/OER hard copies for check out.
3. Student Life: use of computer lounge for student access to OER.
4. Computer Lab: use of computers for student access to OER.
5. DSPS: facility use to assist disabled students using OER.
6. Professional Development: access to campus classrooms/facilities for OER workshops.
Policy Requirements: List any policy requirements that will be necessary to successfully execute your plan.
Example: Make sure academic freedom policies are applied to textbook affordability program
Example: Make sure accessibility policies are applied OER resources
1. Academic Senate reviews BP 4030 Academic Freedom to determine if any OER information needs to be included.
2. Academic Senate reviews BP/AP 4020 Program, Curriculum, and Course Development, to determine if any OER information needs to be included.
3. District Assembly reviews BP/AP 5140 Disabled Student Program and Services, to determine if any OER information needs to be included.
4. Academic Senate reviews BP/AP 3710 Securing of Copyright, to determine if any OER information needs to be included.
5. Academic Senate reviews BP/AP 3715 Intellectual Property, to determine if any OER information needs to be included.
6. Academic Senate reviews BP/AP AP3750 Use of Copyrighted Material, to determine if any OER information needs to included.
7. District Assembly reviews BP/AP 3915 Printing, to determine if any OER information needs to be included.
8. College Council reviews SB 1359 ZTC section reporting procedures.
9. Academic Senate advises College Council regarding the additional reporting of low cost sections in the online schedule of classes in which faculty have partially adapted OER.
10. Academic Senate advises College Council regarding the development of ZTC degree and certificate pathways.
Resource Requirements: List any resource requirements and projected costs that will be necessary to successfully execute your plan. Feel free to add additional rows as needed.
The following district/college areas will provide services to implement some of the objectives of this plan. Costs are embedded within the existing college organization and annual college budget.
1. Professional Development Committee will facilitate OER related professional development activities.
2. Library Support Staff working at the Library Reserve Desk will provide student access to hard copies of OER materials.
3. District Technology Services will provide support for OER activities requiring technical assistance.
4. Help Desk will provide technological support to faculty and students accessing OER materials.
5. District Print Services will provide access to free hard copies of OER for faculty use.
6. District Print Services will provide access to outreach print materials.
Distribution and Dissemination of Grant Funds and Section Savings
Resources to Implement Updated SBVC Textbook Affordability Plan - Funding Request $31,000. Activities incurring financial expenditures can be categorized into three areas associated with TACC stipend, professional development, and and outreach efforts. 1. TACC: 30% 2. Professional Development: 65% 3. Outreach, Marketing, and Printing Costs Not Covered by District Print Shop: 5% Responsibilities of the TACC focus on the implementation and facilitation of OER activities, including outreach, professional development, communication, and reporting requirements. TACC will be supported by a stipend. Costs associated with professional development and networking activities incur the greatest financial costs since they often involve expenses associated with travel and stipends, food and beverages, and event outreach, instructional, and/or organizational materials. The remainder of activities outlined in this plan tend to be in-kind costs embedded within the college and district organization, and therefore do not require any major expenditures. However a small percentage of funding has been allocated for outreach, marketing, and printing costs. Examples of these include brochures, posters, banners, and recognition certificates. The SBVC professional faculty development program and activities will be enhanced by this updated textbook affordability plan through the continuation of OER activities such as discovery of OER, accessibility, licensing, adoption, open pedagogy, and evaluation. Since a major focus of this plan also includes developing a permanent SBVC Textbook Affordability Plan, these additional professional development activities foster a culture associated with OER sustainability. SBVC has both a full time tenured Professional Development Coordinator, a collegial Professional Development Committee, and works with the district technology instructional support team to facilitate technology related professional development activities.
The following are overarching goals of this updated Textbook Affordability Plan: • Increase the use of OER to save students money on textbooks in transfer, basic skills, and vocational courses • Facilitate and support professional development opportunities to assist faculty in the curation, and adoption of OER and open pedagogy • Institutionalize the Textbook Affordability Plan as a permanent working document.
These three areas have the greatest impact on the implementation and sustainability of OER at SBVC during 2018-2020 and beyond given the existing campus culture, organization, resources, and support services. The distribution and dissemination of grant funds to support OER activities and efforts is driven by the fact that a significant percentage of SBVC students have financial needs substantial to qualify for financial. Professional development and outreach activities provide access to OER information, resources, and networking opportunities for both faculty and students. When SBVC students have access to low cost and free instructional materials, this helps to decrease the student equity gap and increase academic success. No part of this request and dissemination of grant funds will be used on activities related to direct compensation for faculty to adopt or create new OER materials, which includes past conversions to OER, development of MOOC’s or online courses that include non-matriculated students, and purchase of new equipment.
Scope of Impact This plan includes a total of 32 sections and at least nine disciplines in which faculty have committed to adopting OER materials with a savings of 30% or more and include openly licensed instructional materials. The 32 sections listed in this updated plan all have a savings of 100% on textbook costs through the use of open educational resources. An approximate total of 984 students or 8% of the headcount of SBVC students will be impacted. The total cost of instructional materials have been reduced by 100% or $203,237. This savings represents a significant financial scope of impact but in particular it is also substantially meaningful given that these sections represents a variety of disciplines. SBVC has demonstrated readiness to continue to increase its sections in which faculty are committed to saving students money on the high cost of textbooks, having exceeded its OER goals in the first round from the original proposed 31 sections to 113 sections submitted in the 2018 final report. This also includes the committment to ensure that students have availability to low cost print copies of OER and computers with internet to access digital OER. Both faculty and student OER data collection will continue by the SBVC Office of Research, Planning and Institutional Effectiveness to ensure proper reporting of OER sections, students served and savings.
Total grant funds requested: | $ | 31000
Add additional rows if needed

## Savings & Progress Report
AB 798 RFP Projected Cost Savings and Progress Report Template Bonus Funding 2018 - 2020
As part of AB798 requirements to receive funding, a campus must show a 30% cost savings. Use columns A - G (blue section) of the spreadsheet to list all courses that will participate in the Adoption Incentive program. All information is required. Use the Campus Progress Report columns (H - K) (green section) when reporting actual savings and costs.
RFP Projected Cost Savings for Proposed Courses (Due with RFP Submission) | [11 empty] | Campus Progress Report (Due: Preliminary Report June 30, 2019 and Final Report June 30, 2020)
Course Identification Number or Prefix | Course Name | Course/Section Number | Estimated Number of Students / Enrollment Cap of Courses Section | Department | Total Cost of Course Materials in Previous Term (at local Bookstore) | Total Cost of Course Materials for All Students in a course in Previous Term (# of students in section X total cost of materials) | Term when OER will be adopted | Estimated Total Cost of Course Materials with adoption of OER | Estimated Total Cost Savings of Course Materials with adoption of OER | Calculating Projected Savings | Projected % Saving | ACTUAL Total Cost of Courses Materials | ACTUAL Cost Savings | Estimated Cost of Printed Materials at Bookstore (if available) | Actual Number of Students Enrolled | Titles of Open Educational Resources Used | Link(s) to OER (if available) | Low Cost Materials Used (if relevant) | Link(s) if available
ACAD 001 | Strategies for College Success | Sec 01 | 40 | Other | 50.75 | 2030 | Fall 2018 | 0 | 2030 | 50.75 | 100%
ASL 109 | American Sign Language | Sec 01 | 35 | Other | 105 | 3675 | Fall 2018 | 0 | 3675 | 105 | 100%
ASL 109 | American Sign Language | Sec 05 | 35 | Other | 105 | 3675 | Fall 2018 | 0 | 3675 | 105 | 100%
BIO 100 | General Biology | Sec 03 | 26 | Science | 202.25 | 5258.5 | Fall 2018 | 0 | 5258.5 | 202.25 | 100%
BIO 100 | General Biology | Sec 04 | 25 | Science | 202.25 | 5056.25 | Fall 2018 | 0 | 5056.25 | 202.25 | 100%
BIO 100 | General Biology | Sec 07 | 26 | Science | 202.25 | 5258.5 | Fall 2018 | 0 | 5258.5 | 202.25 | 100%
BIO 100 | General Biology | Sec 08 | 25 | Science | 202.25 | 5056.25 | Fall 2018 | 0 | 5056.25 | 202.25 | 100%
BIO 109 | History of Life | Sec 01 | 28 | Science | 19.95 | 558.6 | Fall 2018 | 0 | 558.6 | 19.95 | 100%
BIO 109H | History of Life Honors | Sec 01 | 28 | Science | 19.95 | 558.6 | Fall 2018 | 0 | 558.6 | 19.95 | 100%
BIO 155 | Introductory Anatomy and Physiology | Sec 01 | 26 | Science | 247.5 | 6435 | Fall 2018 | 0 | 6435 | 247.5 | 100%
BIO 155 | Introductory Anatomy and Physiology | Sec 02 | 25 | Science | 248 | 6200 | Fall 2018 | 0 | 6200 | 248 | 100%
BIO 155 | Introductory Anatomy and Physiology | Sec 03 | 26 | Science | 247.5 | 6435 | Fall 2018 | 0 | 6435 | 247.5 | 100%
BIO 155 | Introductory Anatomy and Physiology | Sec 04 | 25 | Science | 247.5 | 6187.5 | Fall 2018 | 0 | 6187.5 | 247.5 | 100%
BIO 155 | Introductory Anatomy and Physiology | Sec 05 | 26 | Science | 247.5 | 6435 | Fall 2018 | 0 | 6435 | 247.5 | 100%
BIO 155 | Introductory Anatomy and Physiology | Sec 06 | 25 | Science | 110 | 2750 | Fall 2018 | 0 | 2750 | 110 | 100%
BIO 250 | Human Anatomy and Physiology I | Sec 70 | 28 | Science | 348.25 | 9751 | Fall 2018 | 0 | 9751 | 348.25 | 100%
BIO 251 | Human Anatomy and Physiology II | Sec 01 | 26 | Science | 348.25 | 9054.5 | Fall 2018 | 0 | 9054.5 | 348.25 | 100%
BIO 251 | Human Anatomy and Physiology II | Sec 02 | 25 | Science | 348.25 | 8706.25 | Fall 2018 | 0 | 8706.25 | 348.25 | 100%
BIO 261 | Human Physiology | Sec 01 | 28 | Science | 257 | 7196 | Fall 2018 | 0 | 7196 | 257 | 100%
BIO 261 | Human Physiology | Sec 02 | 25 | Science | 257 | 6425 | Fall 2018 | 0 | 6425 | 257 | 100%
BIO 261 | Human Physiology | Sec 03 | 26 | Science | 257 | 6682 | Fall 2018 | 0 | 6682 | 257 | 100%
BIO 261 | Human Physiology | Sec 04 | 25 | Science | 257 | 6425 | Fall 2018 | 0 | 6425 | 257 | 100%
BIO 261 | Human Physiology | Sec 05 | 26 | Science | 257 | 6682 | Fall 2018 | 0 | 6682 | 257 | 100%
FN 162 | Introduction to Food and Nutrition | Sec 04 | 30 | Other | 203.25 | 6097.5 | Fall 2018 | 0 | 6097.5 | 203.25 | 100%
ENGL 101 | Freshman Composition | Sec 11 | 25 | English | 110.25 | 2756.25 | Fall 2018 | 0 | 2756.25 | 110.25 | 100%
HUMSV 181 | Intro to Alcohol and Drug Studies | Sec 02 | 35 | Other | 237.5 | 8312.5 | Fall 2018 | 0 | 8312.5 | 237.5 | 100%
PSYC 110 | Abnormal Psychology | Sec 70 | 40 | Psychology | 273 | 10920 | Fall 2018 | 0 | 10920 | 273 | 100%
SOC 150 | Aging and the Life Course | Sec 70 | 40 | Sociology | 278.5 | 11140 | Fall 2018 | 0 | 11140 | 278.5 | 100%
SOC 100 | Introduction to Sociology | Sec 30 | 38 | Sociology | 270.25 | 10269.5 | Summer 2018 July 2-August2 | 0 | 10269.5 | 270.25 | 100%
SOC 100 | Introduction to Sociology | Sec 31 | 38 | Sociology | 270.25 | 10269.5 | Summer 2018 July 2-August2 | 0 | 10269.5 | 270.25 | 100%
SOC 100 | Introduction to Sociology | Sec 72 | 40 | Sociology | 270.25 | 10810 | Summer 2018 July 2-August2 | 0 | 10810 | 270.25 | 100%
POLIT 100 | American Politics | Sec 30 | 34 | Political Science | 90.75 | 3085.5 | Summer 2018 July 2-August2 | 0 | 3085.5 | 90.75 | 100%
POLIT 100 | American Politics | Sec 72 | 34 | Political Science | 90.75 | 3085.5 | Summer 2018 July 2-August2 | 0 | 3085.5 | 90.75 | 100%
Total Students |  |  | 984 |  |  | 203237.2 |  | Total Savings | 203237.2
Total Sections |  |  | 32 |  |  |  |  | Total Cost with OER | 0
Average Student Per Section |  |  | 31 |  |  |  |  | Percentage Savings | 100%
[8 empty] | Grant Fund Request | 31000